## Sheet1
Backlog Item | Type | Description | Priority | Order | Status
Create HTML project/file | Task |  | HIGH | 1 | Complete
Create Story | Task |  | HIGH | 2 | In progress
Create use cases | Task |  | HIGH | 3 | Complete
Create homepage design | Task |  | HIGH | 4 | Complete
Create Logo for the game | Task | Logo for the homepage | MEDIUM | 5 | In progress
Create Play/Load of home | Task/Dev |  | HIGH | 6 | Complete
Create HTML template to incorporate story | Task/Dev |  | HIGH | 7 | Complete
Make Play start game | Use case | Play button needs to start the game | HIGH | 8 | Complete
Implement story in game | Task/Dev | Implement the story and the various of options | HIGH | 9 | In progress
Implement karma system | Task/Dev | Implemenet karma system to keep track of good/bad deeds | HIGH | 10
Implement save option in game | Task/Dev | Implement save option in game | HIGH | 11
Implement load to working status | Task/Dev | Make load option load saved files | HIGH | 12
Implement flashy stars in homepage | Task | background will have flashy stars | LOW | 13
Make Play/Load button nicer | Task/Dev | Make Play/Load Buttons with a better design | LOW | 14